Risk-adjusted capacity additions outlook

Purpose

We are developing a project-level method to estimate a plausible range of annual capacity additions from 2026 to 2030 based on GEM’s capacity in development data. The starting point is the GIPT dataset of individual power projects, some with known intended commissioning/start years and some without. The aim is to move from a simple “known pipeline by stated year” view toward an illustrative, risk-adjusted outlook that accounts for uncertainty around project timing, delays, cancellations, and undated projects.

This is not intended to be a precise forecast of individual project delivery. It is an assumption-based simulation designed to show the range of additions that could plausibly materialise from the current project pipeline under transparent assumptions.

1. Core logic

Each row in the GIPT dataset represents an individual project, unit, or phase. For each project, the model asks:

Does this project get delivered, and if so, in what year?

Projects can have one of several outcomes:

- Delivered between 2026 and 2030

- Delayed beyond 2030

- Cancelled

- Excluded from the model, for example pumped hydropower/storage

The model handles projects differently depending on whether they have a known intended start or commissioning year.

Projects with known start years

For projects where Start year is known:

- Use the stated Start year as the baseline delivery year.

- Apply a cancellation probability.

- If not cancelled, sample a delay from the relevant assumptions.

- Assign the project to an adjusted delivery year.

- If the adjusted delivery year falls between 2026 and 2030, add its capacity to that year.

Example:

A 500 MW offshore wind project in pre-construction with a stated start year of 2027 may be cancelled, delivered in 2027, delayed to 2028 or 2029, or pushed beyond 2030 depending on the sampled outcome.

Projects without known start years

For projects where Start year is missing:

- Apply a cancellation probability.

- If not cancelled, sample a plausible remaining time to delivery.

- Sample an additional delay.

- Estimate the delivery year from the current model year.

- If the estimated delivery year falls between 2026 and 2030, add its capacity to that year.

Example:

An undated utility-scale solar project in pre-construction may be assigned a remaining delivery time of two years plus a one-year delay, producing an estimated delivery year of 2029.

2. Input files

The framework uses three main input CSV files.

A. GIPT dataset (Global-Integrated-Power-March-2026-II.xlsx)

This is the main project-level dataset. Required fields currently include:

| Column | Purpose |
| --- | --- |
| GEM unit/phase ID | Unique identifier for the project, unit, or phase |
| Country/area | Used for geography-specific risk multipliers |
| Subregion | Available for later aggregation or assumptions |
| Region | Available for later aggregation or assumptions |
| Capacity (MW) | Capacity added if the project is delivered |
| Status | Current project status: construction, pre-construction, announced |
| Start year | Intended commissioning/start year where known; blank if unknown |
| Type | Broad technology type: wind, utility-scale solar, hydropower |
| Technology | More detailed technology field, used to split onshore and offshore wind |

The script creates additional modelling fields from these inputs.

B. Base assumptions table (base_assumptions.csv)

The base assumptions table defines cancellation and timing assumptions by:

- Scenario

- Technology

- Status

- Whether the start year is known or unknown

The current modelling technology categories are:

- utility-scale solar

- onshore wind

- offshore wind

- hydropower

Wind projects are split into onshore/offshore using the Technology field. If Type is wind and Technology contains off, the project is treated as offshore wind; otherwise it is treated as onshore wind.

The base assumptions table has columns like:

| Column | Purpose |
| --- | --- |
| scenario | Scenario name, currently central |
| technology | Modelling technology category |
| status | Project status |
| date_known | known or unknown |
| cancel_prob | Probability that project is cancelled |
| delay_min | Minimum assumed delay |
| delay_mode | Most likely delay |
| delay_max | Maximum assumed delay |
| undated_remaining_min | Minimum remaining years to delivery for undated projects |
| undated_remaining_mode | Most likely remaining years to delivery for undated projects |
| undated_remaining_max | Maximum remaining years to delivery for undated projects |

The model currently uses triangular distributions for timing assumptions. This is useful because the assumptions are transparent: minimum, most likely, and maximum.

C. Geography multiplier table (geography_multipliers.csv)

The geography multiplier table adjusts the base assumptions for specific geographies.

For now, we are using a simple adjustment based on one of five GEM Regions, with additional treatment for China

Example structure:

| geography_key | cancel_multiplier | delay_multiplier | remaining_time_multiplier |
| --- | --- | --- | --- |
| Global | 1.0 | 1.0 | 1.0 |
| China | 0.5 | 0.7 | 0.8 |

The model applies these multipliers to the base assumptions:

- Final cancellation probability = base cancellation probability × geography cancellation multiplier

- Final delay assumptions = base delay assumptions × geography delay multiplier

- Final remaining time assumptions = base remaining time assumptions × geography remaining time multiplier

This avoids needing a fully crossed assumptions table across country, technology, status, date-known category, and scenario.

3. Data processing steps

Step 1: Read and clean project data

The script reads the project file and standardises key fields:

- Cleans whitespace

- Converts capacity to numeric

- Converts Start year to numeric

- Normalises status values to lower case

- Creates a date_known flag:

  - known if Start year has a value

  - unknown if Start year is blank

Step 2: Exclude pumped hydropower/storage

Projects where the Technology field contains pumped are excluded before modelling.

This is because pumped hydropower/storage is not intended to be included in the current capacity additions outlook.

The script saves excluded rows separately to:

excluded_pumped_hydropower.csv

This allows us to check what was removed.

Step 3: Create modelling technology categories

The script derives a simplified model_technology field:

| Original fields | Model category |
| --- | --- |
| Type = utility-scale solar | utility-scale solar |
| Type = hydropower | hydropower |
| Type = wind and Technology contains off | offshore wind |
| Type = wind and Technology does not contain off | onshore wind |

This allows separate assumptions for onshore and offshore wind.

Step 4: Merge assumptions

The project table is merged with the base assumptions table using:

- model_technology

- Status

- date_known

- scenario

This assigns each project its base cancellation and timing assumptions.

Step 5: Apply geography multipliers

The script creates a geography_key:

- China for projects in China

- Respective Regions for all other projects

It then merges the geography multiplier table and calculates final risk assumptions for each project.

Step 6: Check for missing assumptions

The script checks whether any projects failed to match the assumptions table.

If many projects have missing assumptions, the usual cause is that the assumptions table is missing one or more combinations of:

- Technology

- Status

- Date-known category

For example, if the project data includes offshore wind, announced, unknown-start-year projects, then the assumptions table needs a row for:

offshore wind | announced | unknown

With four technologies, three statuses, two date-known categories, and one scenario, the central assumptions table needs:

4 × 3 × 2 = 24 rows

4. Simulation method

The simulation is run many times. Each run produces one possible future delivery pathway.

For each project in each run:

If the project has a known start year

The model:

- Draws a cancellation outcome.

- If not cancelled, samples a delay.

- Adds the delay to the known start year.

- Assigns the project capacity to the adjusted delivery year if it falls between 2026 and 2030.

If the project has no known start year

The model:

- Draws a cancellation outcome.

- If not cancelled, samples a remaining time to delivery.

- Samples an additional delay.

- Calculates a delivery year from the current model year.

- Assigns the project capacity to that year if it falls between 2026 and 2030.

Projects delivered after 2030 are not counted in the annual additions chart, but they are conceptually treated as delayed beyond the model window rather than necessarily cancelled.

5. Performance note

Vectorised speeds up the Monte Carlo simulation.

6. Outputs

The framework produces several output tables.

A. Prepared project risk input table

prepared_project_risk_inputs.csv

This is a project-level table after cleaning, technology classification, assumption matching, and geography multipliers.

It includes fields such as:

- Project ID

- Country/area

- Region

- Capacity

- Status

- Start year

- Date-known flag

- Model technology

- Base cancellation probability

- Geography multipliers

- Final cancellation probability

- Final delay assumptions

- Final undated remaining-time assumptions

This table is useful for checking whether assumptions were applied correctly before running the simulation.

B. Simulated annual additions by run

simulated_annual_additions_by_run.csv

This is the raw Monte Carlo output after aggregation.

It contains annual delivered capacity by:

- Scenario

- Run ID

- Year

- Status

- Model technology

This is useful for diagnostics and further analysis.

C. Annual additions summary by status and technology

simulated_annual_additions_by_status_summary.csv

This summarises the simulation results across runs by:

- Scenario

- Year

- Status

- Model technology

It includes summary statistics such as:

- Mean capacity

- P10

- P50

- P90

This is the main input for stacked bar charts where bars are broken down by project status and technology.

D. Annual total summary

simulated_annual_additions_total_summary.csv

This sums across all statuses and technologies to show total annual additions by year.

It includes:

- Mean

- P10

- P50

- P90

This is useful for adding uncertainty ranges around total annual additions.

E. Annual total by technology summary

simulated_annual_additions_total_by_technology_summary.csv

This keeps technologies separate but sums across statuses.

It gives annual totals for:

- Utility-scale solar

- Onshore wind

- Offshore wind

- Hydropower

This is useful where we want annual risk-adjusted additions by technology rather than one combined total.

7. Intended visualisation

The current chart uses stacked columns for annual capacity additions, with future additions broken down by status.

For the risk-adjusted outlook, the likely visual approach is:

- Historical additions shown as actual annual additions up to 2025.

- Future years, 2026–2030, shown as simulated/risk-adjusted annual additions.

- Stacked bars broken down by current project status:

  - Construction

  - Pre-construction

  - Announced

- Separate panels or scenario views for low, central, and high delivery assumptions if/when those are added.

- Optional uncertainty shown, for example P10–P90 whiskers or bands, rather than uncertainty within each stack segment.

A useful framing for the chart is:

Historical additions, known pipeline, and illustrative risk-adjusted pipeline outlook.

The language should avoid implying this is a deterministic forecast. Better wording is:

illustrative risk-adjusted pipeline outlook

or

project-level simulation based on transparent assumptions.

8. Possible future extensions

Possible future extensions include:

- Adding low, central, and high delivery scenarios

- Current version uses a direct remaining-time assumption for undated projects. A later refinement could explicitly model time already spent in the current status, allowing old/stale projects to receive different remaining-time, delay, or cancellation assumptions.

- Adding correlated system-level risk so that each simulation run reflects a broader high-delivery or low-delivery environment